# Statement of Work

Zoom Cars Application Development

## March 27, 2024

# Proposal

Customer	Zoom Cars, United Kingdom

Vendor	Tekrowe Digital, Pakistan

Project Name	Zoom Cars Application

SOW Effective Date

This Statement of Work, including its Project-Specific Terms and other attachments applies to the professional services (“Services”) and associated Deliverables defined as tangible items, including any electronic, computer-coded and other intangible form of it, designated as a Deliverable in this SOW to be provided to/for Customer by Tekrowe Digital in connection with the project identified in this SOW.

This SOW is valid only if signed by both parties before:  April 05, 2024

### Zoom Cars	Tekrowe Digital

Signature:	Signature

Printed Name	Printed Name

Title	Title

Date	Date

# PROJECT-SPECIFIC TERMS

## Nature of the Project

### Description of the general nature and scope of the Project

Zoom Cars (www.zoomcars.org) is a Bristol, UK based Taxi firm which is providing commuting and travelling services to the local community through taxis/cabs cars.

To manage the operations effectively Zoom Cars wants to have an eco-system that should provide the better services to its customers to book the ride, and the drivers to know about their bookings and effectively provide the services to the passengers and for the back-office operations team to dispatch the bookings optimally. This eco-system should have following connected applications:

- Consumer Mobile App – to book, cancel and track the rides.

- Driver Mobile App – to get the information of their scheduled and assigned bookings and the destinations.

- Dispatch System – Back-office web based solution to assign the booking optimally to the drivers at the nearest spot.

- Admin Panel – Web based management console to manage the application, its users, their roles, and the fleet.

## Project Duration

The Start Date will be agreed between the parties but shall be no more than two (2) weeks after signature of this document.

The estimated duration of this project is Twenty-Four (24) weeks, at which point all the services provided by Tekrowe, as described in this SOW are expected to be completed assuming no material deviations from the Assumptions, Dependencies and Required Inputs.

The project will be delivered on Agile Development Framework and will be segregated into eight (8) to ten (10) sprints (two to three weeks). After each Sprint a shippable functionality will be deployed on Stage for customer’s validation and then on production environment.

## Services

Scope of this SOW is limited to deliverable/services part only. Tekrowe LLC will provide the following Services. Services may create tangible outputs or have other completion criteria, but only the items identified in this Section of this SOW are formal Project Deliverables.

### Delivery/Project Management Services

Project Management services will be provided for above defined services, as per Tekrowe Project Management Methodology. Tekrowe’s project manager and technical leads will be responsible to deliver the services outlined in this SOW.

The Project Manager’s role includes the following specific responsibilities related to Tekrowe portion of the project:

- Identify and assemble the project team.

- Plan, schedule, and coordinate project activities

- Plan, coordinate and manage activities such as escalation, change control, testing, and acceptance.

- Prepare and conduct periodic status meetings to discuss the project status, schedules, milestones, issues, and forthcoming activities.

- Act as the single point-of-contact for project issues relating to the successful completion of application development.

### Scope

The scope of the engagement is only limited to services/deliverables defined in this section. Zoom Cars has shared its requirements in a meeting at Tekrowe’s Islamabad office, then through a document and through email communications. Tekrowe investigated the requirements and defined following scope for each application and shared with Zoom Cars for their consents:

Zoom Cars Consumer Mobile Application:

- Wireframes designs

- Consumer registration and login

- Ride Booking Implementation – this includes Ride booking, track the taxi on map (Google Map and Waze)

- Payments through Google Pay, Apple Pay and Credit/Debit Cards

- Review and feedback.

- Report lost properties/belongings.

- Report a driver.

- 2-FA Authentication like other apps in the industry

- Social logins

- Zoom Cars Wallet

- My favorites

- In app calling and chatting through Twilio, Agora or similar integrations.

Zoom Cars Basic Dispatch System – Web Application:

- The list of requested bookings

- Auto assignment of booking to the drivers in specific areas/zones

- Manual assignments

- List of available drivers from where controller can assign this booking request to any driver.

Zoom Cars Driver’s Mobile Applications

- Mobile application wireframes designs

- Driver login and forget password.

- 2-FA implementation for drivers

- Ride acceptance journey – this includes the contact passenger through protected number, tracking of passenger location through Google Map and Waze options.

- Payment integration and updates à Cash Collection, Payment from Passenger’s Zoom Wallet, through Credit/Debit Cards, Google and Apple Pay.

- Stats Checking à Check earnings and working hours.

- My rides à scheduled and completed rides.

- In app calling and chatting through Twilio, Agora or similar integrations.

Zoom Cars Admin Panel – Web Application

- Requirements and wireframes

- Authentication settings implementation

- Driver Management

- Zoom Cars user management.

- Role management for authorized accesses to certain features

- Tariff Management

- Fleet Management

- Dashboards and Stats

- Reports à Such as how many hours a driver has been logged on for and the number of app jobs, what the cost and price of those jobs for a particular week is etc.

To implement the above scope, the generalized development services will be:

| 1 | Service Description | Dependency | Required inputs | Completion Criteria |
| --- | --- | --- | --- | --- |
| 3.2.1 Project Planning and setup Services | Tekrowe Delivery Manager will agree with Client’s PM on the project schedule for the project. This will be considered as a baseline for the project. Planning is a time-boxed activity which will not exceed more than 1-week after SOW signing. | Availability of Client’s Project Manager for providing input, identifying Project dependencies, and agreeing the baseline project schedule with Tekrowe PM | Signed SOW | Creation of Baseline project schedule |
| 3.2.2 Requirements Analysis and Definition | Tekrowe PM and Architect will have multiple sessions with Zoom Cars team to get the clarity of all requirements and to convert them into user stories. | Availability of Client’s Project/Product Manager and Business SMEs to provide the functional and non-functional requirements | Signed SOW Availability of Client’s SMEs | Functional and Non-functional requirements documented on Scrum/Kanban Board with backlogs items |
| 3.2.3 Process Mapping and Wireframes Development | Once the functional requirements of the product or specific sprints are defined Tekrowe’s Business Analyst and UI/UX Engineer will create: - Process maps - Wireframes for all applications | Availability of Client’s Project Manager and Business SMEs to provide the functional and non-functional requirements | Defined Requirements | - Process maps readiness - Wireframes readiness |
| 3.2.4 Architecture and Design | Tekrowe will define an optimal enterprise architecture for Zoom Cars: The proposed technology stack is: Development Technologies - NextJS / REACT JS - NestJS - REACT Native - PostgreSQL - REST APIs Deployment: - AWS | - Functional and Non-functional Requirement’s finalization - Availability of technical SME from Client | Requirement’s definition and Wireframes | - Architecture and readiness - Staging environment readiness on AWS Cloud platform - Development environment readiness on GitHub |
| 3.2.5 Zoom Cars Consumer Application Development | Tekrowe project team will develop and test Zoom Cars consumer mobile application according to the defined functional requirements, wireframes and architecture. | - Architecture, design, wireframes, and backend readiness - Staging environment readiness - Development environment readiness - Requirements readiness | - Functional and non-functional requirements - Architecture document - Backend APIs - 3rd party APIs | UAT sign-off of Consumers’ Mobile Application. |
| 3.2.6 Zoom Cars Driver Mobile Application Development | Tekrowe project team will develop and test Zoom Cars drivers’ mobile application according to the defined functional requirements, wireframes and architecture. | - Architecture, design, wireframes, and backend readiness - Staging environment readiness - Development environment readiness - Requirements readiness | - Functional and non-functional requirements - Architecture document - Backend APIs - 3rd part APIs | UAT sign-off of Driver Mobile Application. |
| 3.2.7 Zoom Cars Basic Dispatch System Development | Tekrowe project team will develop and test Zoom Cars dispatch system application according to the defined functional requirements, wireframes and architecture. | - Architecture, design, wireframes, and backend readiness - Staging environment readiness - Development environment readiness - Requirements readiness | - Functional and non-functional requirements - Architecture document - Backend APIs - 3rd part APIs | UAT sign-off of Dispatch System. |
| 3.2.8 Zoom Cars Admin Panel Development | Tekrowe project team will develop and test Zoom Cars admin panel application according to the defined functional requirements, wireframes and architecture. | - Architecture, design, wireframes, and backend readiness - Staging environment readiness - Development environment readiness - Requirements readiness | - Functional and non-functional requirements - Architecture document - Backend APIs - 3rd part APIs | UAT sign-off of Admin Panel Application |
| 3.2.6 Zoom Cars Application Testing and deployment services | After each sprint Tekrowe will deploy the shippable work items on staging environment and integrate with previous sprint work. Tekrowe will perform the System Integration Testing and also assist the client in UAT – and after UAT sign-off the production deployment will be done. | - Readiness of stage and production environment - Readiness of shippable work items after every sprint - Readiness of test cases | - Tested work items in development environment - Completion of functionalities and features for a sprint. | - Completion of SIT - UAT Sign-off - Completion of production deployment. |

### Acceptance

Application periodically deployed in lower environment for testing and validation. After validation Client Team will provide feedback and acceptance. But client will have right to re-evaluate the implementation, change and/or reprioritize the requirements through Change Control process.

### Warranty

Tekrowe Digital offers 30-days warranty from the date of signoff of Final user acceptance or usage of the final application whichever comes first. In case any changes or new requirements are raised during warranty period they will be handled through change control process

### Post Project Support

After final acceptance of the engagement, Tekrowe Digital will provide 30 days support during the Warranty period. If further support is required beyond the Warranty period, Tekrowe Digital offers the following three Services Models for continued support of the system. The costs of either are not included in this contract and will be agreed upon separately.

- Managed Services Model

  - Tekrowe will manage the daily operations of the Application which will include.

    - Cloud Infrastructure management and maintenance

    - Application monitoring and maintenance

  - Help Desk / Call Center

    - L1 support to act as first point of contact for any Service / Application Issues

    - L2 and L3 support for addressing any issues and escalation.

- Team Augmentation

  - Tekrowe can provide technical resources which will be managed by the customer for any system maintenance issues.

- Customized Development

  - Tekrowe Digital will provide custom development services for specific requirements i.e., mobile development, scale up the application.

### 3.6	Future Product Development and feature Development

Tekrowe Digital will provide Software and Product development services needed to further enhance or scale the Application. These will be discussed, negotiated, and agreed in a separate contract.

## Deliverables

The Services and Deliverables to be provided by Tekrowe include only what is expressly described in this SOW and any mutually agreed upon Change Orders, once approved by both parties. It is important to note that a total review period of 3 days has been built into the schedule after which acceptance will be provided by Zoom Cars Team. This review period includes time for reviewing by Zoom Cars, feedback incorporation by Tekrowe and any subsequent review by Zoom Cars for each defined deliverable. A change request will be issued if there is any change to the duration of the review period.  Any additional time required will be subject to change control.

During this review period client will need to advise Tekrowe if the deliverable reasonably:

- Has been reviewed and does meet the signoff approach and criteria, where applicable.

- Has been reviewed and is signed off subject to specific comments.

- Fails to conform to the sign off approach and signoff criteria approved at the outset of the service being provided.

Requests for modifications in the functionality, technical architecture, changes/updates or fixes in the already developed and rolled out solution will be managed through the normal change control procedures.

It will be the responsibility of the client to periodically review the end deliverable before the final acceptance and sign off criteria. It is acknowledged by both Tekrowe and the client that there is a need to ensure required reviews & approval cycles are completed within three working days.

### List of Deliverables

| Deliverables | Description | Deliverable sign off Approach | Party Responsible for Creation | Responsible Resources (Tekrowe/Zoom Cars) | Service/Phase Reference |
| --- | --- | --- | --- | --- | --- |
| 4.1.1 Project Schedule | This document describes the work breakdown structure as per the project scope & Schedule of the project activities – this will be provided in the form of Trello/JIRA Board, and requirements document. | Trello/JIRA board and the document segregating the requirements into different Sprint | Tekrowe | Tekrowe: Delivery Manager Zoom Cars: PM for review and sign-off | Planning Phase |
| 4.1.2 Wireframes | Development of Wireframes | Client Review, feedback and Approval | Tekrowe | Tekrowe: UI/UX Team Zoom Cars: PM | Requirements Analysis and Design |
| 4.1.3 Consumers’ Mobile Applications | Implementation of Solution and Deployment | - All Agreed features mentioned in section 3.2 | Tekrowe | Tekrowe: Development Team Zoom Cars: PM | Development Phase |
| 4.1.4 Drivers’ Mobile Application | Implementation of Solution and Deployment | - All Agreed features mentioned in section 3.2 | Tekrowe | Tekrowe: Development Team Zoom Cars: PM | Development Phase |
| 4.1.5 Basic Dispatch Web Application | Implementation of Solution and Deployment | - All Agreed features mentioned in section 3.2 | Tekrowe | Tekrowe: Development Team Zoom Cars: PM | Development Phase |
| 4.1.6 Admin Panel Web Application | Implementation of Solution and Deployment | - All Agreed features mentioned in section 3.2 | Tekrowe | Tekrowe: Development Team Zoom Cars: PM | Development Phase |
| 4.1.7 Handover | Handover Package | Application Handed over to client upon complete production deployment (including source code on GIT) | Tekrowe | Tekrowe: Development Team Zoom Cars PM | Deployment Phase |

### Completion Criteria

Customer will provide requirements and completion criteria (“Project Requirements”) for all Deliverables and related Services prior to the Project Start date, or as otherwise agreed in the Project Schedule.  Any delays or additional work from incomplete requirements or from failure to meet the Dependencies/Entry Criteria may result in a change to the Project Schedule and additional fees.  Any conflict between the SOW and the Project Requirements or any change to the signed-off Project Requirements will be managed with a Change Order.

### Customer Sign-off

Unless other acceptance criteria are specified in this Statement of Work, Deliverables are considered accepted upon Delivery by Tekrowe. Zoom Cars will provide a sign-off for each deliverable.

## Proposed Architecture and Technology Stack

Tekrowe Engineering team will propose Monolithic Architecture during the planning phase of the project – but following is the targeted Technology Stack and High-Level Design:

Technology Stack:

- NextJS / REACT JS à For Web Application Front End

- NestJS à for Backend

- REACT Native à for Mobile application development. Hybrid technology will work for both Android and iOS with single code base.

- PostgreSQL à Database

- AWS Platform

## Cost and Payment

This is a fixed cost project based on the requirements shared by Zoom Cars during the meeting at Tekrowe Office and later in the document “Copy of Zoom Own Software Requirements.docx” and follow-up email communications.

The overall price of this project is US$ 36,000 (US Dollar Thirty-Six Thousand Only) – and following will be the payment schedule:

| Milestone | Payment |
| --- | --- |
| Requirements Definition, Project Setup Architecture, Wireframes | US$ 500 |
| Completion of Consumers’ Application | US$ 500 |
| Completion of Drivers’ Application | US$ 500 |
| Completion of Dispatch System | US$ 500 |
| Completion of Admin Panel | US$ 500 |
| Handover | US$ 500 |
| Completion of Warranty Period | US$ 500 |

Tekrowe Digital will invoice Zoom Cars after each Milestone sign-off and all payments will be paid in Tekrowe Digital Bank Account (details will be provided at the start of the project).

If Zoom Cars wants to pay in Pakistan Rupees, Tekrowe will invoice each milestone in PKR according to the conversion rate at the time of invoicing – the payment from Pakistan to Pakistan will also have Govt Taxes and GST (that is not included in the price above).

Following payment terms and cost have not been included in the above-mentioned price:

- Govt Taxes

- Cost of Cloud platforms

- Cost of 3rd party APIs like Waze, Google Map, Twilio and any other.

## Dependencies, Responsibilities and Terms & Conditions

Tekrowe Digital and Zoom Cars have the following project responsibilities:

- Tekrowe and Customer agree to each complete all responsibilities in this SOW, the Project schedule, and other mutually agreed project plan documents.

- Tekrowe and Customer will each assign a Project Manager and/or POCs. The project managers/POCs will develop the Project schedule and other project plan documents and processes. These include task and resource management, status reporting, time and expense reporting, invoicing, change control, and issues management.  The issues management process will specify timeframes and responsibilities for escalation to Tekrowe and Customer management as necessary to meet the Project Schedule.

- Tekrowe and Customer will identify the hardware, software, licenses, and capacity / performance specifications for the technical environments required to execute this Project.  These include, but are not limited to, development, stage, production servers and databases, software configuration management, GIT Repository, Trello and defect tracking tools. Customer will be responsible to pay for Cloud fee, Storage fee, deployment fee on AWS OR similar and any 3rd party Software License Fee.

- Customer will articulate the Project Requirements for all Services and Deliverables under this SOW by the Project start date, or as otherwise agreed in the Project schedule including all policies, governance rules, and business, development, and deployment processes.  Once signed-off, any change to Project Requirements will be mutually agreed by the Project Managers using the Change Control process.

- Customer will identify and interpret any applicable laws, regulations, and statutes that affect Customer’s systems or data to which Tekrowe will have access during this Project as well as all policies, governance rules, business processes, development guidelines, and deployment processes which pertain to the Services and Deliverables.  Customer will ensure that its systems and processes comply with any such requirements. These must be disclosed before this SOW is signed and will be managed as Project Requirements.

- Customer will implement, with agreement from Tekrowe, controls on access, use, and security of data, the transmission of personally identifiable information, and appropriate steps to mask sensitive data.  Customer will provide information about, and qualified resources to describe, all source data.  Customer will ensure the completeness, accuracy, quality, consistency, format, and integrity of the data and is responsible for resolving any data quality problems.  Customer will provide samples of data including any necessary masking or protection of sensitive information, as required to support Services and Deliverables and according to the Project Schedule.

- Customer will identify and provide all needed APIs for any 3rd party integrations like Google Maps, Waze, Twilio, Google Pay, Apple Pay, Credit/Debit Card APIs

- Customer will provide the documentation of all 3rd Party APIs (if any)

- Customer will inform Tekrowe immediately about any changes/updates in 3rd party APIs (if any) which might impact the Project.

- Customer shall own and provide the prioritized product requirements (functional, non-functional), product and technology roadmaps.

- Customer’s product management and business teams will keep grooming the product backlog and will do the periodic meetings with product development team to review and finalize the requirements

- Tekrowe’s Solution Architect will design the solution and suggest the technology stack – the approval and ownership will remain with Zoom Cars.

- Tekrowe will be responsible to assemble the Engineering Team, office space, internet, developer machines/laptops, Office 365 and Microsoft Teams for collaboration – If client preferred to have any other collaboration tool, then will provide the subscriptions.

- Tekrowe team will work from Monday to Friday, 10:00AM to 6:00PM Pakistan Time and Tekrowe management will ensure the availability.

- Tekrowe team will inform about their vacation plan, legal holidays in advance and missing days will be covered before overall engagement ends.

- Zoom Cars will not directly hire any existing or previous member(s) of Tekrowe’s project team during the engagement and six months after the engagement. However, Team Buy-in option can be done on agreed terms between Tekrowe and Zoom Cars Managements ONLY after this contract will expire.

- Tekrowe’s Delivery Leader will share the weekly status report that will provide the overall progress of the project.

## Scope Exclusions

- The Services to be provided by Tekrowe include only what is expressly described in this SOW and any mutually agreed upon Change Orders.

- Modifications/Enhancements of any existing systems unless mutually agreed

- Development/Enhancement of any 3rd party APIs

- Upgrades of any hardware, software, or server unless Tekrowe will be asked and given the access to cloud environment.

- Performing software upgrades for workstations, including but not limited to Operating System upgrades.

- Scope of support during warranty period will be limited to bug fixing only. Any deviation from the agreed and implemented requirements, rules or scenarios not captured in design specification or issues due to data quality will not be considered bugs, any other change (i.e., change in requirement/Design, change due to lack of clarity in requirements) will be handled through standard change control process.

## Intellectual Property

The rights to all Intellectual Property developed as a part of this engagement resides solely with the Customer. Source code, design and any relevant documentation will be handed over to the client after completion of the project and payments.

## Confidentiality and Non-Disclosure Agreement

- Each Party acknowledges that in the course of the performance of this Contract it may obtain Confidential Information of the other Party.  The Receiving Party shall, at all times, both during the term of this Contract and thereafter for a period of two keep in confidence and trust all of the Disclosing Party’s Confidential Information received by it. The Receiving Party shall not use the Confidential Information of the Disclosing Party other than as necessary to fulfill the Receiving Party’s obligations or to exercise the Receiving Party’s rights under the terms of this Contract. The Receiving Party shall take reasonable steps to prevent unauthorized disclosure or use of the Disclosing Party’s Confidential Information and to prevent it from falling into the public domain or into the possession of unauthorized persons, but in no event shall the Receiving Party use less care than it would in connection with its own Confidential Information of like kind.  The Receiving Party shall not disclose Confidential Information of the Disclosing Party to any person or entity other than its officers, employees and consultants who need access to such Confidential Information in order to affect the intent of this Contract and who have entered into confidentiality agreements which protect the Confidential Information of the Disclosing Party sufficiently to enable the Receiving Party to comply with this Section.

- Permitted Disclosures.  Nothing in this Contract shall prevent the Receiving Party from disclosing Confidential Information to the extent that Receiving Party is legally compelled to do so by any governmental investigative or judicial agency pursuant to proceedings over which such agency has jurisdiction; provided always, that prior to any such disclosure, the Receiving Party shall (i) assert the confidential nature of the Confidential Information to the agency; (ii) to the extent permitted by applicable law, immediately notify the Disclosing Party in writing of the agency’s order or request to disclose; and (iii) cooperate fully with the Disclosing Party in protecting against any such disclosure and/or obtaining a protective order narrowing the scope of the compelled disclosure and protecting its confidentiality. Either Party may provide a copy of this Contract to the following persons and/or entities who are under obligations of confidentiality substantially similar to those set forth in this Contract:  potential acquirers or investors and to their employees, agents, attorneys, investment bankers, financial advisors and auditors in connection with the due diligence review of such Party.  Either Party also may provide a copy of this Contract to: (i) the Party’s public accounting firm in connection with the quarterly and annual financial or tax audits, and (ii) to the Party’s outside legal advisors in connection with obtaining legal advice relating to this Contract, the relationship established by this Contract or any related matters, provided that they are also under obligations of confidentiality substantially similar to those set forth in this Contract.